## Sheet1
Backlog item ID	Backlog item story	Story	Task owner	Initial estimate	Week 1	Week 2	Week 3
1	user want to register an account	design user interface	Florian	2	2	0	0
		implement back-end code		4	2	1	0
		implement front-end code		2	2	2	0
		complete unit testing		1	1	0	0
2	user want to login	design user interface	Florian	3	2	1	0
		implement back-end code		2	2	0	0
		implement front-end code		5	1	0	0
		complete unit testing		1	1	0	0
3	user want to logout	design user interface	Florian	3	2	1	0
		implement back-end code	Florian	2	2	0	0
		implement front-end code		3	1	0	0
		complete unit testing		2	2	2	0
4	user want to modify his account	design user interface	Florian	1	0	0	0
		implement back-end code		3	2	1	0
		implement front-end code		4	2	0	0
		complete unit testing		3	1	0	0
5	user want to delete his account	design user interface	Florian	2	2	2	0
		implement back-end code		1	1	0	0
		implement front-end code		5	2	1	0
		complete unit testing		2	2	0	0
6	user want to create player card	design user interface	Florian	3	1	0	0
		implement back-end code		1	0	0	0
		implement front-end code		3	1	0	0
		complete unit testing		3	2	2	0
7	user want to update his player card	design user interface	Florian	2	1	1	0
		implement back-end code		3	2	1	0
		implement front-end code		2	2	0	0
		complete unit testing		3	1	0	0
8	user want to delete his player card	design user interface	Florian	2	2	2	0
		implement back-end code		1	0	0	0
		implement front-end code		3	2	1	0
		complete unit testing		2	2	0	0
9	user want to sort players by rank	design user interface	Florian	3	1	0	0
		implement back-end code		2	2	2	0
		implement front-end code		1	0	0	0
		complete unit testing		3	2	1	0
10	user want to sort players by server	design user interface	Florian	2	2	0	0
		implement back-end code		3	1	0	0
		implement front-end code		2	2	2	0
		complete unit testing		1	0	0	0